## requirements
ReqID | Category | User | Requirement | Dependencies | Priority | TimeEstimate
1 | must | System | The system must have a database connection so that user information can be stored within the site. | None | 10 | 3
2 | must | Guests | Guests must accept terms and conditions to create an account so that the site owners are not held liable for clauses mentioned within it. | None | 10 | 2
3 | must | Registered | Members and moderators must be able to create an account from which to access the site so that others cannot access their data. | 2 | 10 | 2
4 | must | Guests | Guests must be able to create an account with their personal credentials so that they can gain member permissions. | 3 | 10 | 1
5 | must | Moderators | Moderators must be able to ban members who are misusing the site, so that the site remains appropriate and reliable. | 3 | 10 | 3
6 | must | System | The system must be able to verify member and moderator usernames and passwords on login against corresponding username and password combinations in the database so that the appropriate, valid registered account is logged into. | 3 | 10 | 2
7 | must | System | The system must allow members and moderators to change their password so they can reset it if they forget it. | 6 | 10 | 2
8 | must | Registered | Members and moderators must be able to log out of their account so others cannot access their data from their computer. | 6 | 10 | 2
9 | must | System | The system must ensure that duplicate accounts are not allowed to be created to prevent people from making multiple accounts and overloading event availability. | 3 | 10 | 2
10 | must | Registered | Moderators and members must be able to add postings so that others can see their events. | 3 | 10 | 6
11 | must | Registered | Moderators and members must be able to update their postings so that others can see their events with correct, up-to-date information. | 10 | 10 | 2
12 | must | Registered | Moderators and members must be able to delete their postings so that others can see if their event was cancelled or removed. | 10 | 10 | 2
13 | must | Moderators | Moderators must be able to delete member event postings that falsely represent events so that the site can have legitimacy. | 12 | 10 | 2
14 | must | Users | All users must be able to view event details so that they know the what, when, and where of the events. | 10 | 10 | 1
15 | must | System | The system must keep track of all the events at a given time, so that users can view specific events and details. | 10 | 10 | 2
16 | must | Registered | Members and moderators must be able to rate events after they have attended them so others can see how well they went. | 10 | 20 | 3
17 | must | Users | All users must be able to see the ratings of events so that they can evaluate their quality in choosing events. | 16 | 20 | 2
18 | must | System | The system must show a map of the Guelph area with some visual indication of the locations of events so that users have geographical context for where they are taking place. | 10 | 20 | 4
19 | must | Users | All users must be able to see where events are happening on the map so they can see what is going on near them. | 18 | 20 | 2
20 | must | Users | All users must be able to search all events so that they can find a specific event of interest to them. | 15 | 20 | 2
21 | must | Registered | Members and moderators must be able to RSVP to events so that they can confirm their attendance. | 10 | 20 | 2
22 | must | System | The system must keep track of the number of open spots for a given event based off of member and moderator RSVPs to track attendance and availability. | 21 | 20 | 3
23 | must | Users | All users must be able to see the number of spots open for an event so that they can know if they are able to register for them or not. | 22 | 20 | 1
24 | must | Moderators | Moderators must be able to update other members' event postings so that the site remains free of misinformation and hate speech. | 11 | 20 | 2
25 | must | Moderators | Moderators must be able to add words to a filter list to keep hateful or inappropriate language from showing up on the site without being censored. | 3 | 30 | 2
26 | must | Registered | Members and moderators must be able to update their profile settings so they can update outdated information. | 3 | 30 | 2
27 | must | System | The system must be AODA compliant so that the website is accessible to all types of users. | None | 30 | 0
28 | must | System | The system must provide text alternatives for videos and images to allow for users with disabilities to access these forms of media. | None | 30 | 0
29 | must | Registered | Members and moderators must be able to add a thumbnail image for their events so that they are recognizable at a glance. | 10 | 30 | 2
30 | must | Registered | Members and moderators must be able to remove their RSVP to events so they can indicate that they are no longer attending. | 21 | 30 | 1
31 | should | Registered | Members and moderators should be able to view their current RSVP'd events on a calendar so that they can see at a glance what events are upcoming. | 21 | 30 | 3
32 | should | Registered | Members and moderators should be able to bookmark events so they can more easily keep track of events they may want to attend in the future. | 10 | 30 | 3
33 | should | Registered | Members and moderators should be able to add indicators to their posts about the type of activity involved so users can easily search for events that interest them. | 20 | 30 | 2
34 | should | Users | All users should be able to filter search results by tag indicators so that they can find events relevant to their interests. | 33 | 30 | 2
35 | should | Moderators | Moderators should be able to suspend accounts so that they can discipline inappropriate actions while allowing users a chance to regain their permissions. | 3 | 30 | 3
36 | should | Moderators | Moderators should be able to un-suspend accounts so that they can give users access to their accounts back following good behaviour. | 35 | 30 | 1
37 | should | Members | Members should be able to readily view moderator contact information so that they can send them more detailed report information if they so wish. | 3 | 30 | 0.5
38 | should | System | The system should provide a crash report if the website crashes so that users can fix any potential issues with their computer that may have caused it. | None | 30 | 3
39 | should | Reporting | Guests and members should be able to report inappropriate or false events so that moderators can be informed of them and deal with them accordingly. | 10 | 30 | 3
40 | should | System | The system should stop members and moderators from creating more than 5 events per day so as to prevent events from overloading the database. | 10 | 30 | 3
41 | should | Registered | Members and moderators should be able to sign up on a waitlist for a full event so that they are able to register for it if a spot opens. | 22 | 30 | 3
42 | should | Users | All users should be able to select map event locations so they can see more details about the event, such as description, time and date, and availability. | 18 | 30 | 3
43 | should | System | The system should have differentiated map indicators depending on the availability or lack thereof of events so that map users can tell at a glance what events have open spots. | 22 | 40 | 3
44 | should | Registered | Members and moderators should be able to add a website link to their posting so that guests and other members can access their event information directly. | 10 | 40 | 1
45 | should | Users | All users should be able to see how intense an activity is so they know if it's the right difficulty for their current fitness level and/or mood. | 33 | 40 | 2
46 | should | System | The system should be able to respond to a search query in under 5 seconds so that the user can quickly find the events they are searching. | 20 | 40 | 1
47 | should | Users | All users should be able to specify how many listings should be viewable on screen at once so that they are not overwhelmed by too many results at once. | 15 | 40 | 2
48 | should | System | The system should be programmed to run the site as expected on all web browsers so that it can be accessible to everyone. | None | 40 | 0
49 | should | Moderators | Moderators should be able to promote members to moderator status and permissions so that the site can scale the number of people running it as needed. | 3 | 40 | 1
50 | should | Moderators | Moderators should be able to demote other moderators in order to prevent or put a stop to abuse of moderator permissions. | 3 | 40 | 1
51 | could | Moderators | Moderators could be able to swap to a member view of the website to help with troubleshooting member issues. | 3 | 40 | 2
52 | could | Moderators | Moderators could modify thumbnail images to ensure that they are all appropriate. | 29 | 40 | 1
53 | could | Moderators | Moderators could be able to see member login history to monitor suspicious activity in accounts. | 3 | 40 | 5
54 | could | Registered | Members and moderators could be able store past events as templates so they can be used for recurring events. | 10 | 40 | 5
55 | could | System | The system could be able to store ratings from past events so that they are viewable by users if the events reoccur. | 54 | 40 | 2
56 | could | Registered | Members and moderators could be able to track how many events they have participated in so that they can track their exercise habits. | 21 | 40 | 3
57 | could | Registered | Members and moderators could be able to track the intensity indicators of their past attended events so that they can track the effectiveness of their exercise. | 33 | 40 | 3
58 | could | Registered | Members and moderators could view their current bookmarks on a calendar so they can see at a glance what events are upcoming. | 32 | 40 | 5
59 | could | Registered | Members and moderators could receive a confirmation email after they RSVP to an event so they can get a reminder about the event they signed up for. | 21 | 40 | 5
60 | could | System | The system could accommodate mobile screen dimensions so that the site is easy to use on mobile devices. | 10 | 40 | 5
61 | could | Users | All users could be able to change the theme of the site to dark mode for easier viewing in low light. | 2 | 50 | 3
62 | could | Users | All users could be able to change the site's language so they can view all pages in their most fluent language. | 2 | 50 | 3
63 | could | Members | Members could be allowed to activate an "adult mode" so that they can see filtered words if desired for context. | 25 | 50 | 3
64 | could | System | The system could have different map indicators to differentiate between the intensities of events. | 33 | 50 | 3
65 | could | Registered | Members and moderators could be able to output all events to a file to be able to compare dates and descriptions easily. | 15 | 50 | 5
66 | won't | System | The system won't be able to view exact user locations so that private information is not stashed on the site. |  |  | 0
67 | won't | System | The system won't allow payments to occur on the website to prevent scams and potential money laundering. |  |  | 0
68 | won't | System | The system won't store data past 60 days to prevent overloading data stores. |  |  | 0
69 | won't | System | The system won't be able to see events outside of Guelph so that our system does not overload the site's data stores. |  |  | 0
70 | won't | Guests | Guests won't be able to comment under posts to minimize potential hateful spam on event listings. |  |  | 0
71 | won't | Reporting | Guests and members won't be able to directly message other members or guests so that hateful interactions do not occur. |  |  | 0
72 | won't | Moderators | Moderators won't be able to turn off adult filtering so that they can immediately see when something isn't filtered if it should be. |  |  | 0
73 | won't | System | The system won't show event postings 1 week past the event date to avoid confusing users about what can be attended, but to allow time to rate events. |  |  | 0
74 | won't | Guests | Guests won't be able to create events to prevent users that do not have contact information registered with the system (which would prevent moderators from contacting them) from creating inappropriate events. |  |  | 0
75 | won't | Registered | Members and moderators won't be able to add a profile picture so as to avoid people potentially adding copyrighted of inappropriate images as profile photos. |  |  | 0

## users
User Types | Definition | Permissions
Members | Members are users who have logged in to the system with their personal credentials, but do not have moderator (administrative) permissions. | Members can add, review, sign up for, search, filter, bookmark, and report events. They can also tag events (say by type or difficulty) for easy searching, and edit and delete their own events.
Guests | Guests are users who have not logged in to the system and/or have not given their personal credentials. This is the default user type assigned when one first goes to the site. | Guests can only search, filter (by existing tags), report, and view events.
Moderators | Moderators are users who have logged in to the system with their personal credentials, and have or were given administrative permissions by other moderators. | Moderators can add, review, sign up for, search, filter, bookmark, and review member reports for events. They can promote others to moderator status, deactivate misused member or moderator accounts, and delete reported and/or inappropriate reports. They can also tag events (say by type or difficulty) for easy searching, and can edit and delete all events as needed.
Users | Hybrid user type used to refer to all 3 user types (guest, member, moderator) collectively.
Registered | Hybrid user type used to refer to members and moderators collectively.
Reporting | Hybrid user type used to refer to members and guests collectively.

## definitions
Users | Hybrid user type used to refer to all 3 user types (guest, member, moderator) collectively.
Registered | Hybrid user type used to refer to members and moderators collectively.
Reporting | Hybrid user type used to refer to members and guests collectively.
Bookmark | To save an event to a separate list for later easier access without signing up to that event (yet).
Tag | To add an identifier (ex. difficulty or category of activity) to an event for search filtering purposes.
RSVP | To sign up for an event.
Crash | When the website stops working as expected.
Thumbnail image | A small image representative of an event.
To be held liable | To be held legally responsible for the consequences of some (user) action.
Adult mode | A version of the website in which censored words are not visibly covered or blocked.

## timeline
halfday | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
day | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 16 | 16 | 17 | 17 | 18 | 18 | 19 | 19 | 20 | 20
Iteration | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
P1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 15 | 15 | 15 | 15 | 11 | 11 | 11 | 11 | 19 | 19 | 19 | 19 | 26 | 26 | 26 | 26 | 42 | 42 | 42 | 42 | 42 | 42
P2 | 2 | 2 | 2 | 2 |  |  |  |  | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 33 | 33 | 33 | 33 | 34 | 34 | 34 | 34
P3 |  |  |  |  | 3 | 3 | 3 | 3 | 9 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 14 | 14 | 17 | 17 | 17 | 17 | 25 | 25 | 25 | 25 | 39 | 39 | 39 | 39 | 39 | 39 | 46 | 46
P4 |  |  | 38 | 38 | 38 | 38 | 38 | 38 | 10 | 10 | 10 | 10 | 10 | 10 | 50 | 50 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 24 | 24 | 24 | 24 | 29 | 29 | 29 | 29 | 32 | 32 | 32 | 32 | 32 | 32 | 37
P5 | [8 empty] | 49 | 49 | 10 | 10 | 10 | 10 | 10 | 10 | 21 | 21 | 21 | 21 | 20 | 20 | 20 | 20 | 30 | 30 | 40 | 40 | 40 | 40 | 40 | 40 | 41 | 41 | 41 | 41 | 41 | 41 | 44 | 44